## Sheet1
Owner | Project name | Customer name | Payment ratio | Supplying / completed | Completion date | Contract terms | Cumulative output value | Cumulative settlement | Cumulative collections | Contract receivable | Total receivable | Collection plan | Received | Secured | Likely | Possible | Total | Gap | Collection rate on output value | Collection rate on settlement | Project ID | Customer code | Reporting month | Product name | Contract unit price | Current advance funding | Advance funding ratio
Wang Lei | Riverside Resettlement Housing Phase II | Demo Construction Engineering, Branch No. 1 | 80% | Supplying | 2024-12-31 | Monthly settlement: 80% of the month's settlement by the 25th of the next month, up to 90% at topping-out, 97% at final settlement, the 3% retention after one year | 12772695 | 10588305 | 9781000 | 807305 | 2991695 |  | 9781000 | 323000 | 202000 | 121000 | 10427000 | 161305 | 76.58% | 92.38% | PRJ2024011 | CUST0103 | 2024-07 | C30 | 390 | 2991695 | 23.42%
Li Na | Hi-Tech Park Plant Building No. 3 | Demo Urban Construction Group Co., Ltd. | 80% | Supplying | 2025-03-31 | Monthly settlement: 80% of the month's settlement by the end of the next month, up to 95% at completion acceptance, the 5% retention within two years | 8281845 | 6297547.5 | 5525000 | 772547.5 | 2756845 |  | 5525000 | 309000 | 193000 | 116000 | 6143000 | 154547.5 | 66.71% | 87.73% | PRJ2024017 | CUST0211 | 2024-07 | C35 | 405 | 2756845 | 33.29%
Wang Lei | Municipal Road Upgrade Lot 1 | Demo Municipal Engineering Co., Ltd. | 70% | Supplying | 2024-10-31 | Monthly settlement: 70% within 60 days of settlement, up to 95% once the final account audit is done | 6364000 | 5482930 | 3137000 | 2345930 | 3227000 |  | 3137000 | 938000 | 586000 | 352000 | 5013000 | 469930 | 49.29% | 57.21% | PRJ2024023 | CUST0156 | 2024-07 | C40 | 430 | 3227000 | 50.71%
Zhao Min | No. 2 Experimental School Extension | Demo Education Construction Co., Ltd. | 80% | Winding down | 2024-08-15 | Monthly settlement: 80% of the month's settlement the next month, up to 97% within three months of completion | 10029057.5 | 9509115 | 8728000 | 781115 | 1301057.5 |  | 8728000 | 312000 | 195000 | 117000 | 9352000 | 157115 | 87.03% | 91.79% | PRJ2023098 | CUST0089 | 2024-07 | C30 | 385 | 1301057.5 | 12.97%