## Sheet1
Owner | Project name | Customer name | Payment ratio | Supplying / completed | Completion date | Contract terms | Cumulative output value | Cumulative settlement | Cumulative collections | Contract receivable | Total receivable | Collection plan | Received | Secured | Likely | Possible | Total | Gap | Collection rate on output value | Collection rate on settlement | Project ID | Customer code | Reporting month | Product name | Contract unit price | Current advance funding | Advance funding ratio
Wang Lei | Riverside Resettlement Housing Phase II | Demo Construction Engineering, Branch No. 1 | 80% | Supplying | 2024-12-31 | Monthly settlement: 80% of the month's settlement by the 25th of the next month, up to 90% at topping-out, 97% at final settlement, the 3% retention after one year | 13744224 | 11234976 | 10540000 | 694976 | 3204224 |  | 10540000 | 417000 | 208000 | 104000 | 11269000 | -34024 | 76.69% | 93.81% | PRJ2024011 | CUST0103 | 2024-07 | C30 | 448 | 3204224 | 23.31%
Li Na | Hi-Tech Park Plant Building No. 3 | Demo Urban Construction Group Co., Ltd. | 80% | Supplying | 2025-03-31 | Monthly settlement: 80% of the month's settlement by the end of the next month, up to 95% at completion acceptance, the 5% retention within two years | 9090034 | 6806867 | 6049000 | 757867 | 3041034 |  | 6049000 | 455000 | 227000 | 114000 | 6845000 | -38133 | 66.55% | 88.87% | PRJ2024017 | CUST0211 | 2024-07 | C35 | 466 | 3041034 | 33.45%
Wang Lei | Municipal Road Upgrade Lot 1 | Demo Municipal Engineering Co., Ltd. | 70% | Supplying | 2024-10-31 | Monthly settlement: 70% within 60 days of settlement, up to 95% once the final account audit is done | 6773600 | 5761394 | 3336000 | 2425394 | 3437600 |  | 3336000 | 1455000 | 728000 | 364000 | 5883000 | -121606 | 49.25% | 57.9% | PRJ2024023 | CUST0156 | 2024-07 | C40 | 494 | 3437600 | 50.75%
Zhao Min | No. 2 Experimental School Extension | Demo Education Construction Co., Ltd. | 80% | Winding down | 2024-08-15 | Monthly settlement: 80% of the month's settlement the next month, up to 97% within three months of completion | 10379928.5 | 9781657 | 8999000 | 782657 | 1380928.5 |  | 8999000 | 470000 | 235000 | 117000 | 9821000 | -39343 | 86.7% | 92% | PRJ2023098 | CUST0089 | 2024-07 | C30 | 443 | 1380928.5 | 13.3%