## Sheet1
Owner | Project name | Customer name | Payment ratio | Supplying / completed | Completion date | Contract terms | Cumulative output value | Cumulative settlement | Cumulative collections | Contract receivable | Total receivable | Collection plan | Received | Secured | Likely | Possible | Total | Gap | Collection rate on output value | Collection rate on settlement | Project ID | Customer code | Reporting month | Product name | Contract unit price | Current advance funding | Advance funding ratio
Wang Lei | Riverside Resettlement Housing Phase II | Demo Construction Engineering, Branch No. 1 | 80% | Supplying | 2024-12-31 | Monthly settlement: 80% of the month's settlement by the 25th of the next month, up to 90% at topping-out, 97% at final settlement, the 3% retention after one year | 10588305 | 8384805 | 8018000 | 366805 | 2570305 |  | 8018000 | 147000 | 92000 | 55000 | 8312000 | 72805 | 75.73% | 95.63% | PRJ2024011 | CUST0103 | 2024-06 | C30 | 390 | 2570305 | 24.27%
Li Na | Hi-Tech Park Plant Building No. 3 | Demo Urban Construction Group Co., Ltd. | 80% | Supplying | 2025-03-31 | Monthly settlement: 80% of the month's settlement by the end of the next month, up to 95% at completion acceptance, the 5% retention within two years | 6297547.5 | 4515750 | 4242000 | 273750 | 2055547.5 |  | 4242000 | 110000 | 68000 | 41000 | 4461000 | 54750 | 67.36% | 93.94% | PRJ2024017 | CUST0211 | 2024-06 | C35 | 405 | 2055547.5 | 32.64%
Wang Lei | Municipal Road Upgrade Lot 1 | Demo Municipal Engineering Co., Ltd. | 70% | Supplying | 2024-10-31 | Monthly settlement: 70% within 60 days of settlement, up to 95% once the final account audit is done | 5482930 | 4558215 | 2693000 | 1865215 | 2789930 |  | 2693000 | 746000 | 466000 | 280000 | 4185000 | 373215 | 49.12% | 59.08% | PRJ2024023 | CUST0156 | 2024-06 | C40 | 430 | 2789930 | 50.88%
Zhao Min | No. 2 Experimental School Extension | Demo Education Construction Co., Ltd. | 80% | Supplying | 2024-08-15 | Monthly settlement: 80% of the month's settlement the next month, up to 97% within three months of completion | 9509115 | 8642865 | 8174000 | 468865 | 1335115 |  | 8174000 | 188000 | 117000 | 70000 | 8549000 | 93865 | 85.96% | 94.58% | PRJ2023098 | CUST0089 | 2024-06 | C30 | 385 | 1335115 | 14.04%